## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 快速问诊 | 作为一个病人，我希望能快速咨询自身情况，以便于加深我对自身情况的了解。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 快速搜索医生 | 作为一个病人，我希望能够通过医生名、医生主治等搜索医生，以便于快速定位需要找的医生。 | Initial Feature | Not Done | 1 | 96 |  |  | 1 | 0
3 | 1 | 1 | user story | 快速搜索药品 | 作为一个病人，我希望能够通过药品名称、药品规格等搜索药品，以便于快速找到所需药品。 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 资深医生推荐 | 作为一个病人，我希望能够有一个资深医生推荐，以便于减轻我选医生的困惑。 | Initial Feature | Not Done | 1 | 93 |  |  | 1 | 0
5 | 1 | 1 | user story | 问诊记录 | 作为一个病人，我希望能够将自己的问诊的记录保存起来，以便于以后按日期查看。 | Initial Feature | Not Done | 1 | 93 |  |  | 2 | 0
6 | 1 | 1 | user story | 医生收藏 | 作为一个病人，我希望可以将自己喜欢的医生加入收藏列表，以便于以后更方便地找到该医生。 | Initial Feature | Not Done | 0.5 | 90 |  |  | 1 | 0
7 | 1 | 1 | user story | 药品收藏 | 作为一个病人，我希望可以将自己需要的药品加入收藏列表，以便于以后更方便地找到该药品。 | Initial Feature | Not Done | 2 | 90 |  |  | 2 | 0
8 | 1 | 1 | user story | 网银充值 | 作为一个病人，我希望可以通过网银快速充值资金。 | Initial Feature | Not Done | 3 | 88 |  |  | 3 | 0
9 | 1 | 1 | user story | 发表文章 | 作为一个病人，我希望能够将自己想要分享的知识或者事件发表出来，以便于给其他病人参考。 | Initial Feature | Not Done | 0.5 | 85 |  |  | 1 | 0
10 | 1 | 1 | user story | 购物车 | 作为一个病人，我希望能够将需要的药品加入购物车，以便于后续付款。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
11 | 1 | 1 | user story | 订单列表 | 作为一个病人，我希望可以将购买的药品加入订单列表，以便于查看订单的详情。 | Initial Feature | Not Done | 1 | 70 |  |  | 1 | 0
12 | 1 | 1 | user story | 文章评论 | 作为一个病人，我希望可以在其他医生或病人发表的文章下评论，以便于和他们进行交流。 | Initial Feature | Not Done | 1 | 65 |  |  | 1 | 0
13 | 1 | 1 | user story | 帮助与反馈 | 作为一个病人，我希望能将遇到的问题和对药品或者医生的反馈发布出去。 | Initial Feature | Not Done | 1 | 60 |  |  | 1 | 0
19
Note on A4: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B4: Luc Segers: This is the release where the story will be developped
Note on C4: Luc Segers: This is the sprint where the story will be developped
Note on D4: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F4: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G4: Luc Segers: Type of the story.
Note on H4: Luc Segers: Status of the story
Note on I4: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J4: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L4: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M4: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N4: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O4: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P4: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information